## Features
Features backlog
ID | Capability | Backlog Item (Feature or Story) | Comments | Phase | Tshirt Sizing | Story Points | Business Uncertainty | Technical Complexity | BEST CASE | MOST LIKELY | WORST CASE | CONE of Uncertainty | Tshirt Size for Cone Calc
1 | User interface | Registration Form |  | Later | M | 8 | Low | Low | 8 | 8 | 8 | 0% | M
2 | User interface | Login |  | Later | M | 13 | Low | Low | 13 | 13 | 13 | 0% | M
3 | User interface | Viewing dashboards (graphics and tables) |  | Later | L | 20 | Low | Medium | 13 | 20 | 27 | 35% | L
4 | Data management | Automatic data analysis |  | Later | L | 20 | Low | Medium | 13 | 20 | 27 | 35% | L
5 | Data management | User database |  | Later | L | 20 | Medium | Medium | 12 | 20 | 28 | 40% | L
6 | Data management | Generation of reports |  | Next | S | 5 | Low | Medium | 4.75 | 5 | 5.25 | 5% | S
7 | Data source | Enterprise database |  | Next | XL | 40 | High | High | 8 | 40 | 72 | 80% | XL
8 | Data source | Large data support |  | Next | M | 8 | Low | Low | 8 | 8 | 8 | 0% | M
Total | 8 | [7 empty] | 79.75 | 134 | 188.25 | 24.38%

## Features Analysis
Phase: | Next
Features analysis by Size | [5 empty] | Features analysis by Uncertainty |  |  |  |  | Features analysis by Complexity
Row Labels | %tage | Number of Uss | Best Case (SP) | Most Likely (SP) | Worst Case (SP) | Row Labels | %tage | Best Case (SP) | Most Likely (SP) | Worst Case (SP) | Row Labels | %tage | Best Case (SP) | Most Likely (SP) | Worst Case (SP)
XS | 0% | 0 | 0 | 0 | 0 | Low | 24.53% | 12.75 | 13 | 13.25 | Low | 15.09% | 8 | 8 | 8
S | 9.434% | 1 | 4.75 | 5 | 5.25 | Medium | 0% | 0 | 0 | 0 | Medium | 9.434% | 4.75 | 5 | 5.25
M | 15.09% | 1 | 8 | 8 | 8 | High | 75.47% | 8 | 40 | 72 | High | 75.47% | 8 | 40 | 72
L | 0% | 0 | 0 | 0 | 0 | Total | 100% | 20.75 | 53 | 85.25 | Total | 100% | 20.75 | 53 | 85.25
XL | 75.47% | 1 | 8 | 40 | 72
XXL | 0% | 0 | 0 | 0 | 0
Total | 100% | 3 | 20.75 | 53 | 85.25

## Cone of Uncertainty
| Project timeline | No of Sprints in Build Phase | Total no of Sprint including (setup, UAT ..) | Y
| Best Case | 0 | 0 | 0
|  | 24 | 44 | 10
| Most Likely | 0 | 0 | 0
|  | 27 | 47 | 10
| Worst Case | 0 | 0 | 0
|  | 30 | 50 | 10
| Threshold | 0 | 0 | 10
|  | 27 | 28 | 10
Build | Average Velocity(SP) per Sprint | 20
Operate | Number of sprints for Operate (handover, releases, UAT, SIT, application support, etc.) | 10
Technical Items | 1. Environment setup for teams (install tools, access to cloud services etc.) 2. Create all environments needed by the engagement: dev, system test, pre-prod, production. 3. Create a delivery pipeline. 4. NFRs 5. Security testing | 10
Visual Parameters
| Cone Size | 6
| Threshold | 10
| Length of threshold | 20
Note on D13: [Comentario encadenado] Su versión de Excel le permite leer este comentario encadenado; sin embargo, las ediciones que se apliquen se quitarán si el archivo se abre en una versión más reciente de Excel. Más información: https://go.microsoft.com/fwlink/?linkid=870924 Comentario: Add Avg Velocity for the Team(s) that will implement the features
Note on D14: [Comentario encadenado] Su versión de Excel le permite leer este comentario encadenado; sin embargo, las ediciones que se apliquen se quitarán si el archivo se abre en una versión más reciente de Excel. Más información: https://go.microsoft.com/fwlink/?linkid=870924 Comentario: If needed please add here any effort for the UAT / Preparation for Go-Live. If more granularity is needed then “whole” sprints, please mark this as zero and add in the ‘Features Analysis’ sheet a line with the needed effort
Note on D15: [Comentario encadenado] Su versión de Excel le permite leer este comentario encadenado; sin embargo, las ediciones que se apliquen se quitarán si el archivo se abre en una versión más reciente de Excel. Más información: https://go.microsoft.com/fwlink/?linkid=870924 Comentario: add if needed. If this is part of the Discovery - you will not needed

## byUncertainty (hidden)
Phase | (All)
Business Uncertainty / Size | %tage | Best Case (SP) | Most Likely (SP) | Worst Case (SP)
Low | 19.58% | 75.65 | 101.5 | 127.35
Medium | 27.19% | 83.8 | 141 | 198.2
High | 53.23% | 69.7 | 276 | 482.3
Total | 100% | 229.15 | 518.5 | 807.85

## byComplexity (hidden)
Phase | (All)
Technical Complexity / Size | %tage | Best Case (SP) | Most Likely (SP) | Worst Case (SP)
Low | 42.91% | 117.3 | 222.5 | 327.7
Medium | 49.37% | 103.85 | 256 | 408.15
High | 7.715% | 8 | 40 | 72
Total | 100% | 229.15 | 518.5 | 807.85

## Assumtions
# | Assumptions
1
2
3
4
5
6
7
8
9
10
11
12

## Definition of Done
This template uses an average velocity (Story Points) to calculate the cone of uncertainty (duration interval). For that to be valid you'll need the estimation team to allign on what "done" means and what activities are included. The below is an example as a starting points and should be tailored case-by-case
Development
Technical Implementation Plan confirmed with architects/TL [if needed].
Code written and tested locally.
Unit Tests developed for Back-end ( 80% code coverage) and Front-end ( 60% code coverage).
Code reviewed and approved by at least one mandatory approval.
Documentation of model/controllers/sequence diagrams [if needed].
IDs for FE elements ( where needed). - checked on code review & testing.
Configuration check - (if needed ) added in release notes.
Release notes updated.
Sonar execution on review - no critical issues accepted.
English labels available in CMS ( if needed).
All defects reported by testing fixed.
Deployment/Demo
Changes deployed successfully to Openshift Director env (no build error + sonar passed successfully ) >= 5 SP (2 days before sprint ends), only bug fixing will be allowed.
Deployment freeze also 3 hours before demo.
Testing
Test cases written in Zephyr.
Application tested against the mock layer, including error cases and edge.
Manual functional test 100% test coverage on test environment.
Manual test (basic and advanced) cases executed and passing.
Exploratory testing executed.
Testing passed 100% on Test Environment.
All issues reported as bugs and linked to the stories.
Acceptance criteria fulfilled.
Test data is documented.
NFR fulfilled.
Quality Acceptance.
No issues with severity worse than Major.
Feature documented in TBD owner.
User story is updated with latest information/requirements.
Automated testing
Automated tests written.
Automated tests committed to Git.
Automated tests executed and validated.
Other considerations
(TBD story by story
OR add a separate story)
*all to be covered with Acceptance criteria.
Performance.
Security.
Error handling.
Localization.
In-house usability testing.

## Team Shape
Delivery Team(s) Shape
Name of Person (if known) | Role | Grade
| Scrum Master | CL
| Senior Developer | SC
| Developer | SE
| Developer | SE
| Senior Tester | CL
| Tester | EN
| Architect | SC
| Project Manager | CL
| Business Analyst | CL

## ConeOfUncertainty Setup
Value | Business Uncertainty Low | Business Uncertainty Medium | Business Uncertainty High | Sizing GoldieLocks: Tshirt to SP Average Lookup |  | Business Uncertainty Values | Phases
zero | 0% | 0% | 0% | zero | 0 | Low | Next
XS | 0% | 5% | 10% | XS | 1.5 | Medium | Later
S | 0% | 10% | 20% | S | 4 | High | Last
M | 0% | 20% | 25% | M | 10.5 |  | (All)
L | 20% | 25% | 30% | L | 20
XL | 25% | 30% | 40% | XL | 40
XXL | 30% | 40% | 50% | XXL | 100
Value | Technical Complexity Low | Technical Complexity Medium | Technical Complexity High | Sizing GoldieLocks: Tshirt to SP Average Lookup |  | Technical Complexity Values
zero | 0% | 0% | 0% | 0 | zero | Low
XS | 0% | 0% | 5% | 1 | XS | Medium
S | 0% | 5% | 10% | 2 | XS | High
M | 0% | 10% | 20% | 3 | S
L | 10% | 15% | 30% | 5 | S
XL | 15% | 20% | 40% | 8 | M
XXL | 20% | 40% | 50% | 13 | M
|  |  |  | 20 | L
|  |  |  | 40 | XL
|  |  |  | 100 | XXL
Note on G2: [Comentario encadenado] Su versión de Excel le permite leer este comentario encadenado; sin embargo, las ediciones que se apliquen se quitarán si el archivo se abre en una versión más reciente de Excel. Más información: https://go.microsoft.com/fwlink/?linkid=870924 Comentario: The cone of uncertainty based on statistical data for a product You could adjust these value with your statistics if needed
Note on L2: [Comentario encadenado] Su versión de Excel le permite leer este comentario encadenado; sin embargo, las ediciones que se apliquen se quitarán si el archivo se abre en una versión más reciente de Excel. Más información: https://go.microsoft.com/fwlink/?linkid=870924 Comentario: M size correspont to 8 or 13 SP the average is 10.5
Note on P2: [Comentario encadenado] Su versión de Excel le permite leer este comentario encadenado; sin embargo, las ediciones que se apliquen se quitarán si el archivo se abre en una versión más reciente de Excel. Más información: https://go.microsoft.com/fwlink/?linkid=870924 Comentario: Possible values for Business Uncertainty
Note on T2: [Comentario encadenado] Su versión de Excel le permite leer este comentario encadenado; sin embargo, las ediciones que se apliquen se quitarán si el archivo se abre en una versión más reciente de Excel. Más información: https://go.microsoft.com/fwlink/?linkid=870924 Comentario: Phase when we plan to implement the feature
Note on P11: [Comentario encadenado] Su versión de Excel le permite leer este comentario encadenado; sin embargo, las ediciones que se apliquen se quitarán si el archivo se abre en una versión más reciente de Excel. Más información: https://go.microsoft.com/fwlink/?linkid=870924 Comentario: Possible values for Technical Complexity